Countryside Conservancy Strategic Plan • 2007-2009

Vision for the Region

Corridors of green connect the population centers in and near the Tunkhannock Creek Watershed.  Conserved open space, farms, forests, and scenic and recreational areas form corridors that enhance the quality of life in the region.  Development is guided by sound planning that accounts for the natural assets of the region.  Residents appreciate and support the infrastructure of green and know that it makes this area one of the best places to live and raise a family.

Vision for the Countryside Conservancy

The Countryside Conservancy has unique characteristics defined by the topography and demographics of the Tunkhannock Creek Watershed.  We are a forward-looking, courageous organization tackling huge issues of resource use and quality of life.

We have been working to build a green infrastructure which simultaneously preserves the quality of our environment and the quality of human life, by drawing upon a diverse and dynamic board, well-trained staff and a strong membership.

We recognize the interdependency between our waterways, population centers and recreation areas.  Our intent is to strengthen these connections using riparian corridors, agrarian areas, greenways, trails and open space.  Our project selection criteria emphasize these connections.

Of equal importance to the Countryside Conservancy are (1) the preservation of natural resources and (2) connecting people to these resources and their neighboring towns.  Including the crucial human elements of land and water conservation in our mission gives the Countryside Conservancy relevance and vibrancy to all citizens of our region, and gives us the capacity to include diverse interest groups.

Core Values

Good Stewards:	We are selective in accepting or acquiring only properties which meet our land acquisition criteria; we take responsibility for monitoring the lands we protect.

Financially Viable:	We engage in activities to ensure our long-term success as an organization.

Responsive:	We actively respond to all inquiries for potential land protection, donations, and for membership.  We seek to identify at-risk properties before they come up for sale.

Organizational Excellence:	We are a professionally-managed organization using the best practices for the operations of non-profits and land trusts and are accountable for the quality of our work.

Benefiting the Community:	The objectives of our organization are aligned with the desires of our membership and the larger community we operate in.

Mission

The Countryside Conservancy protects lands and waters in and near the Tunkhannock Creek Watershed for the public benefit now, and for the future.

### Goals, Strategies and Actions

## Conservation Goal:  Land and water “hubs” of high conservation importance in and around the Tunkhannock Creek Watershed are identified and protected, and are connected by protected “spokes.”  Other open lands and waters meeting Conservancy criteria are protected as the opportunity arises.

## Strategies:

## Identify land and water “spokes” and “hubs” of highest conservation importance and protect them.

## Continue to work to protect other lands and waters as opportunities arise.

## Continue improving stewardship of lands and waters owned by the Conservancy, and monitoring and defense of easements held by the Conservancy.

## Advocate for better laws, policies and planning to support land and water conservation in the region.

## Financial Goal:  The Conservancy marks steady growth in financial assets to support its operations and programs.

## Strategies:

## Manage the Conservancy’s financial assets appropriately to meet the objectives of this Plan.

## Develop and implement a Fundraising Plan and policies to support the Conservancy in achieving this Plan’s goals, strategies and actions.

## Build Board and staff leadership and plan for succession in fundraising.

## Increase financial support from a wider community of individuals and businesses.

## Selectively seek and implement grants that fit into this Plan.

## Human Resources and Organization Goal:  The Conservancy is a well-run organization with a diverse and dynamic board, well trained staff, and engaged core of volunteers.

## Strategies:

## Enhance Board recruitment process, and establish a process to guide Board succession.

## Enhance staff strengths in public communications, community visibility, fundraising, land project management, office management, and bookkeeping.

## Establish a strong program for volunteer recruitment, management and recognition.

## Enhance organizational planning and achieve LTA accreditation.

## Community Connections Goal:  The Conservancy is an active participant in land use discussions for the benefit of the community.

## Strategies:

## Improve public relations and outreach efforts in the community we serve.

## Build relationships with local governments for support in land conservation and to help promote good planning.

## Assist and support other entities (governmental, non-profit, community) that are working to protect important lands and waters.

Abbreviations:

“ED”:	Executive Director

“LM&S Committee”: 	Land Management & Stewardship Committee

“L&WP Committee”: 	Land & Water Protection Committee

“PM”:	Program Manager (Cheryl Ellsworth)

## Conservation Goal:

## Land and water “hubs” of high conservation importance in and around the Tunkhannock Creek Watershed are identified and protected, and are connected by protected “spokes.”  Other open lands and waters meeting Conservancy criteria are protected as the opportunity arises.

# Strategy 1:	Identify land and water “spokes” and “hubs” of highest conservation importance and protect them.

| 2007 | 2008 | 2009 |
| --- | --- | --- |
| Develop a Conservation Plan for the Tunkhannock Creek Watershed that identifies and ranks high priority lands for conservation Responsible party: Working group under L&WP Committee Results: __________ | Review and revise project selection criteria based on Conservation Plan Responsible party: Working group under L&WP Committee Results: __________ | Hold at least one public meeting or seminar to present information on land and water conservation to landowners in selected areas Responsible party: ED and L&WP Committee Results: __________ |
| Obtain tax maps, aerial photography and digitized data to identify key lands and waters and their owners Responsible party: Land staff Results: __________ | Contact landowners neighboring Little Rocky Glen to assess their interest in protecting or donating their lands Responsible party: Land staff and members of L&WP Committee Results: __________ | Review and re-assess Conservation Plan to determine if it is providing the needed guidance Responsible party: L&WP Committee Results: __________ |
| Select priority sites and proactively approach individual landowners about protecting their lands; start discussions Responsible party: Land staff and members of L&WP Committee Results: __________ | Draw up list of landowners surrounding Lackawanna State Park & contact them to assess their interest in protecting their lands Responsible party: Land staff and members of L&WP Committee Results: __________ | Reassess progress on Trolley Trail and review priority ranking of individual segments Responsible party: L&WP Committee with staff support Results: __________ |
| Review progress on Trolley Trail from Clarks Summit to Lake Winola, and prioritize individual segments to pursue Responsible party: L&WP Committee with staff support Results: __________ | Put out feelers to landowners not previously contacted along the trolley right-of-way Responsible party: L&WP Committee with staff support Results: __________ |  |

Outcomes:

By end 2008, finalize agreements for 2 miles of Trolley Trail in Clarks Summit-Dalton area.

By end 2009, finalize agreements for 1 mile of Trolley Trail in La Plume/Factoryville area.

## Conservation Goal:

## Land and water “hubs” of high conservation importance in and around the Tunkhannock Creek Watershed are identified and protected, and are connected by protected “spokes.”  Other open lands and waters meeting Conservancy criteria are protected as the opportunity arises.

# Strategy 2:	Continue to work to protect other lands and waters as opportunities arise.

| 2007 | 2008 | 2009 |
| --- | --- | --- |
| Review LTA Standards and Practices relating to land project management, assess Conservancy’s compliance. Responsible party: Land staff supported by PM Results: __________ | Develop staff capacity in approaching landowners and drafting easements, to lighten volunteer workload Responsible party: Land staff Results: __________ | Make follow-up contact with landowners who have been contacted but not made a decision about protecting their land Responsible party: Land staff and members of L&WP Committee Results: __________ |
| Review open land files and update information, contact landowners to assess whether they remain interested; cull certified “dead” land projects. Responsible party: Land staff Results: __________ | Develop a landowner outreach information packet Responsible party: L&WP Committee, ED and land staff Results: __________ |  |
| Respond to and work with landowners who contact the Conservancy independently (ongoing) Responsible party: Land staff supported by L&WP Committee Results: __________ |
| Assess progress on ongoing land projects; close new projects as rapidly as feasible (ongoing) Responsible party: Land staff supported by L&WP Committee Results: __________ |

## Conservation Goal:

## Land and water “hubs” of high conservation importance in and around the Tunkhannock Creek Watershed are identified and protected, and are connected by protected “spokes.”  Other open lands and waters meeting Conservancy criteria are protected as the opportunity arises.

# Strategy 3:	Continue improving stewardship of lands and waters owned by the Conservancy, and monitoring and defense of the Conservancy’s easements.

| 2007 | 2008 | 2009 |
| --- | --- | --- |
| Review closed land files for missing or incomplete information, such as project approval documents; fill in any gaps Responsible party: Land staff Results: __________ | Develop easement violation policy and easement amendment policy Responsible party: L&WP Committee Results: __________ | Develop a team of legal professionals who are informed and trained on easement issues and will work with the Conservancy; provide training opportunities for them Responsible party: L&WP Committee/Board Results: __________ |
| Develop policy on acceptance of lands donated to the Conservancy, including associated stewardship contributions Responsible party: L&WP Committee supported by land staff Results: __________ | Digitize key land-file data and store offline; develop off-site fireproof storage for key original land documents such as deeds and easements Responsible party: Land staff Results: __________ | Expand programmed public use of Conservancy preserves, e.g. nature walks Responsible party: Land staff supported by Outreach Committee Results: __________ |
| Complete posting and signage of Conservancy preserves; discuss with landowners and create an easement-signage program Responsible party: Land staff supported by LM&S Committee Results: __________ | Publicize existence and accessibility of Conservancy preserves Responsible party: ED & Land staff Results: __________ | Develop method for tracking changes in ownership of easement properties Responsible party: Staff and Board Results: __________ |
| Meet with landowners to develop and implement easement-signage program Responsible party: Land staff and LM&S Committee Results: __________ | Develop strategy for communicating with neighbors of Conservancy preserves and enlisting them as volunteer stewards Responsible party: Land staff supported by LM&S Committee Results: __________ |  |
| Develop and implement policy on communicating with easement landowners and easement neighbors Responsible party: L&WP Committee Results: __________ | Complete management plans for all preserves owned and managed by the Conservancy Responsible party: Land staff supported by LM&S Committee Results: __________ |  |
| Monitor all easements held by the Conservancy at least once per year (ongoing) Responsible party: Land staff Results: __________ |
| Review management plans for all Conservancy-owned properties annually, develop annual work plans and implement (ongoing) Responsible party: Land staff supported by LM&S Committee Results: __________ |

## Conservation Goal:

## Land and water “hubs” of high conservation importance in and around the Tunkhannock Creek Watershed are identified and protected, and are connected by protected “spokes.”  Other open lands and waters meeting Conservancy criteria are protected as the opportunity arises.

# Strategy 4:	Advocate for better laws, policies and planning to support land and water conservation in the region.

| 2007 | 2008 | 2009 |
| --- | --- | --- |
| Communicate with county authorities about valuation of properties under conservation easements and agricultural easements Responsible party: L&WP Committee Results: __________ | Visit Harrisburg to meet with key DCNR and other officials, to present the Conservancy and our priorities Responsible party: ED and Board Results: __________ |  |
| Be an advocate in all three counties for lower property taxes on lands under conservation easement Responsible party: ED and Board Results: __________ |  |  |
| Support important initiatives of the LTA and PALTA with letters to legislators, newspaper pieces, etc. (ongoing) Responsible party: ED and Board Results: __________ |

## Financial Goal:

## The Conservancy marks steady growth in financial assets to support its operations and programs.

# Strategy 1:	Manage the Conservancy’s financial assets appropriately to meet the objectives of this Plan.

| 2007 | 2008 | 2009 |
| --- | --- | --- |
| Review LTA Standards and Practices relating to financial management, assess Conservancy’s compliance Responsible party: Board supported by PM Results: __________ | Provide staff with training opportunities in QuickBooks accounting and related software Responsible party: ED Results: __________ | Review financial plans and investment activities; adjust as needed to meet the Conservancy’s needs Responsible party: Finance Committee Results: __________ |
| Create an Investment Committee and develop an investment policy for funds held by the Conservancy Responsible party: Finance Committee Results: __________ | Review and enhance tracking of grants and funds in QuickBooks Responsible party: PM Results: __________ |  |
| Review assets in land & easement stewardship funds, and adequacy for long-term needs; make plans to address any shortfall. Responsible party: Finance Committee Results: __________ | Begin implementing investment policy Responsible party: Finance Committee supported by staff Results: __________ |  |
| Review and monitor financial policies for the sound fiscal management of the Conservancy (ongoing) Responsible party: Finance Committee supported by PM Results: __________ |

## Financial Goal:

## The Conservancy marks steady growth in financial assets to support its operations and programs.

# Strategy 2:	Develop and implement a Fundraising Plan and policies to support the Conservancy in its Strategic Plan goals, strategies and actions.

| 2007 | 2008 | 2009 |
| --- | --- | --- |
| Develop 3-year Fundraising Plan to include plans for managing and growing funding sources including: major donors, membership, Auction, planned giving, endowments, and grants Responsible party: Working group appointed by Fundraising Committee Results: __________ | Implement Fundraising Plan recommendations Responsible party: ED and Fundraising Committee Results: __________ | Review and update Fundraising Plan Responsible party: Fundraising Committee Results: __________ |
| Create information packet on planned giving; distribute to individuals and estate planners Responsible party: ED supported by Fundraising Committee & Finance Committee Results: __________ | Develop list of local professionals knowledgeable about trusts and financial planning to whom we can refer prospective donors Responsible party: Board and ED Results: __________ | Develop and implement gift acceptance policy, donor recognition policy and other policies needed to guide fundraising Responsible party: ED, PM and Fundraising Committee Results: __________ |
| Troubleshoot and improve donor database to ensure it can store and deliver the information we need Responsible party: Staff, with consultant support as needed Results: __________ | Establish endowments with local foundations Responsible party: Executive Committee, Finance Committee and ED Results: __________ |  |

## Financial Goal:

## The Conservancy marks steady growth in financial assets to support its operations and programs.

# Strategy 3:	Build Board and staff leadership and plan for leadership succession in fundraising.

| 2007 | 2008 | 2009 |
| --- | --- | --- |
| Provide staff training in fundraising. Responsible party: Staff/use outside consultant as needed Results: __________ | Identify and cultivate fundraising leaders within the Fundraising Committee. Responsible party: Board supported by ED Results: __________ | Assess fundraising skills of Board and Advisory Board members. Responsible party: ED and Board Results: __________ |
| Train Board members in basic fundraising skills. Responsible party: Board/use outside consultant as needed Results: __________ |  | Assess staff capacity and the need for dedicated development staff. Responsible party: ED Results: __________ |
| Add individuals with fundraising expertise to Board or Advisory Board. Responsible party: Board Results: __________ |  |  |

## Financial Goal:

## The Conservancy marks steady growth in financial assets to support its operations and programs.

# Strategy 4:	Increase financial support from a wider community of individuals and businesses.

| 2007 | 2008 | 2009 |
| --- | --- | --- |
| Seek new members from cooperating non-profit organizations and other sources Responsible party: ED Results: __________ | Do a ZIP-code targeted fundraising mailing in an area where the Conservancy has completed a high-profile project Responsible party: ED supported by Fundraising Committee Results: __________ | Review demographics of our region, assess where additional effort can be placed to increase membership Responsible party: ED and Fundraising Committee Results: __________ |
| Trial-run a joint event with a non-profit organization not directly competing with the Conservancy, to cross-fertilize membership Responsible party: Outreach Committee supported by staff Results: __________ | Establish regular email and Web contact with donors and members Responsible party: ED, supported by outside consultant as needed Results: __________ |  |
| Review Conservancy database to identify overlooked individuals who should be approached for donations Responsible party: Fundraising Committee, staff Results: __________ | Begin regularly approaching corporate donors in the area for contributions Responsible party: Board and ED Results: __________ |  |
| Develop list of businesses in the area to approach for financial contributions Responsible party: ED, Fundraising Committee, Advisory Board Results: __________ |  |  |

## Financial Goal:

## The Conservancy marks steady growth in financial assets to support its operations and programs.

# Strategy 5:	Selectively seek and implement grants that fit into this Plan.

| 2007 | 2008 | 2009 |
| --- | --- | --- |
| Use Nonprofit Community Action Center & other local resources to identify new private and corporate foundations to approach Responsible party: ED Results: __________ | Review all grants received to date; identify grantmakers to approach again Responsible party: ED supported by Fundraising Committee Results: __________ | Review the Conservancy’s needs and strategize grant-seeking for future years Responsible party: Fundraising Committee and ED Results: __________ |
| Develop list of grant-fundable projects based on this Plan Responsible party: ED Results: __________ | Meet with foundations that have provided repeated or ongoing support; assess their priorities and wishes against this Plan Responsible party: ED and Fundraising Chair Results: __________ |  |
| Get commitment from at least 2 foundations for multi-year challenge grants to build capacity Responsible party: ED and Executive Committee Results: __________ |  |  |
| Review open grants to ensure smooth and timely implementation, assess cost-effectiveness (ongoing) Responsible party: ED Results: __________ |
| Monitor state and Federal government grant programs that could support this Plan, pursue where appropriate (ongoing) Responsible party: ED, Fundraising Committee; consultant as needed Results: __________ |

## Human Resources and Organization Goal:

## The Conservancy is a well-run organization with a diverse and dynamic board, well trained staff, and engaged core of volunteers.

# Strategy 1:	Enhance Board recruitment process, and establish a process to guide Board succession.

| 2007 | 2008 | 2009 |
| --- | --- | --- |
| Review diversity of Board membership, assess against diversity of the community we serve Responsible party: Board Development Committee Results: __________ | Update Board manual and institutionalize procedures for Board member orientation Responsible party: Board Development Committee Results: __________ | Review makeup of Advisory Board, assess against the diversity of the community we serve Responsible party: Board Development Committee Results: __________ |
| Provide outreach and training to Advisory Board members Responsible party: Board Development Committee and ED Results: __________ |  |  |
| Identify key skills needed on the Board, actively recruit Board prospects to fill these gaps Responsible party: Board Development Committee and staff Results: __________ |  |  |
| Review LTA Standards and Practices for Board governance management, assess compliance; develop new policies and practices as needed Responsible party: PM and Board Development Committee Results: __________ |  |  |
| Review Conservancy bylaws and committee structure annually (ongoing) Responsible party: Board Development Committee (Michael Kane) Results: __________ |
| Send at least 2 Board members to LTA Rally or other relevant training each year (ongoing) Responsible party: Board Results: __________ |
| Identify and cultivate new Board prospects on a rolling basis (ongoing) Responsible party: Board and Advisory Board Results: __________ |
| Appoint Vice-Chairs for all committees to create line of succession for committee leadership. (ongoing) Responsible party: Board President supported by Board Development Committee Results: __________ |

## Human Resources and Organization Goal:

## The Conservancy is a well-run organization with a diverse and dynamic board, well trained staff, and engaged core of volunteers.

# Strategy 2:	Enhance staff strengths in public communications, community visibility, land project management, office management, and bookkeeping.

| 2007 | 2008 | 2009 |
| --- | --- | --- |
| Review LTA Standards and Practices relating to staff, assess Conservancy’s compliance; develop new policies and practices as needed (including Personnel Policy) Responsible party: ED and PM; Board Results: __________ | Assess staffing (number of staff, duties, and hours worked) against Conservancy workload; recommend any changes needed Responsible party: ED Results: __________ |  |
| Provide staff training in Access software Responsible party: Staff Results: __________ | Review and update all staff job descriptions Responsible party: Staff, supported by Executive Committee/Board President Results: __________ |  |
| Add new staff member in 2007 to lead land project management Responsible party: ED Results: __________ |  |  |
| Send at least 1 staff member to LTA Rally, PALTA conference or other relevant training each year (ongoing) Responsible party: Staff Results: __________ |

## Human Resources and Organization Goal:

## The Conservancy is a well-run organization with a diverse and dynamic board, well trained staff, and engaged core of volunteers.

# Strategy 3:	Establish a strong program for volunteer recruitment, management and recognition.

| 2007 | 2008 | 2009 |
| --- | --- | --- |
| Revive “Volunteer of the Year” award Responsible party: Outreach Committee Results: __________ | Develop plan for volunteer recruitment, management and recognition Responsible party: Volunteer Coordinator and ED Results: __________ | Start implementing volunteer management plan Responsible party: Volunteer Coordinator and ED Results: __________ |
| Appoint a Volunteer Coordinator to work with staff in recruiting, managing and thanking volunteers Responsible party: Outreach Committee/Board Results: __________ | Start tracking number of active volunteers and hours worked each year (including Board) Responsible party: Staff and Board Results: __________ | Hold an annual event specifically targeted at thanking volunteers Responsible party: Volunteer Coordinator supported by staff Results: __________ |

## Human Resources and Organization Goal:

## The Conservancy is a well-run organization with a diverse and dynamic board, well trained staff, and engaged core of volunteers.

# Strategy 4:	Enhance organizational planning and achieve LTA accreditation.

| 2007 | 2008 | 2009 |
| --- | --- | --- |
| Review LTA Standards and Practices in preparation for applying for LTA accreditation. Responsible party: PM and Board Results: __________ | Apply for LTA accreditation (may extend to 2009). Responsible party: PM and ED supported by Board Results: __________ |  |
| Develop policies and procedures required by LTA Standards and Practices (example: Records Policy; policy on sale or transfer of land). Responsible party: Board supported by staff Results: __________ | Develop criteria to guide engagement in projects that are not strictly land conservation: public policy, planning, regulatory matters, etc. Responsible party: Board supported by staff Results: __________ |  |
| Review goals and functions of Watershed Coalition within the Conservancy. Responsible party: Board President and ED Results: __________ |  |  |
| Review this Plan in December each year and extend to cover an additional year. Responsible party: Board supported by staff Results: __________ |

## Community Connections Goal:

## The Conservancy is an active participant in land use discussions for the benefit of the community.

# Strategy 1:	Improve public relations and outreach efforts in the community we serve.

| 2007 | 2008 | 2009 |
| --- | --- | --- |
| Expand website to include more Conservancy information and links; update monthly Responsible party: ED with consultant/volunteer support Results: __________ | Host 5 or more public events on Conservancy lands (trail walks, picnic, nature education, “drive-in” movie, etc.) Responsible party: Outreach Committee supported by staff Results: __________ | Review “Success Measures” and use them in PR to promote our growth and success Responsible party: ED Results: __________ |
| Establish Speaker’s Bureau and schedule at least 4 public presentations before other local organizations each year Responsible party: Outreach Committee and ED Results: __________ | Develop a “Guide’s Bureau” of volunteers who can lead nature walks several times per year Responsible party: Outreach Committee and ED Results: __________ | Develop list of outdoor recreational associations in the region ; reach out to these groups via guest speakers, field trips to Conservancy lands, etc. Responsible party: ED and Outreach Committee Results: __________ |
| Create a simple brochure for use with general public, and a more detailed one for use with landowners, grantmakers, etc. Responsible party: ED with working group of Outreach Committee Results: __________ | Create a short video to be used for public presentations, at Conservancy events, etc. Responsible party: ED with working group of Outreach Committee/outside consultant Results: __________ |  |
| Set following year’s calendar of public events before the end of the current year (ongoing) Responsible party: Outreach Committee and ED Results: __________ |

## Community Connections Goal:

## The Conservancy is an active participant in land use discussions for the benefit of the community.

# Strategy 2:	Build relationships with local governments for support in land conservation and to help promote good planning.

| 2007 | 2008 | 2009 |
| --- | --- | --- |
| Obtain updated contact information for local government officials Responsible party: Administrative staff Results: __________ | Organize a public event with media presence to get public officials to a project site Responsible party: Outreach Committee Results: __________ | Review local planning and zoning efforts throughout the watershed; contribute to discussions where appropriate Responsible party: ED and L&WP Committee Results: __________ |
| Add key government officials and representatives at local, county and state levels to Conservancy event invitation lists Responsible party: Staff Results: __________ | Explore options for convening gatherings of municipal officials Responsible party: ED and Board Results: __________ |  |
|  | Identify and build partnerships with municipal advisors (solicitors, engineers, COGs, etc.) Responsible party: ED and Board Results: __________ |  |
| Meet annually with each county’s planning commission and board of commissioners, and with federal or state elected officials and representatives (ongoing) Responsible party: ED and Executive Committee Results: __________ |

## Community Connections Goal:

## The Conservancy is an active participant in land use discussions for the benefit of the community.

# Strategy 3:	Assist and support other entities (governmental, non-profit, community) that are working to protect important lands and waters.

| 2007 | 2008 | 2009 |
| --- | --- | --- |
| Start a program of meeting at least twice yearly with County farmland preservation agents and conservation district managers Responsible party: ED, L&WP Committee chair Results: __________ | Assist counties and State in publicizing and promoting Agricultural Security Areas and state’s agricultural preservation program Responsible party: ED Results: __________ | Support community efforts to develop Environmental Advisory Committees Responsible party: ED & Watershed Coalition Results: __________ |
| Start a program of meeting yearly with County commissioners and state legislators for the watershed area, to communicate our priorities and concerns Responsible party: Board Results: __________ | Draft a plan for cooperating with other land trusts and non-profit organizations in the region Responsible party: Executive Committee Results: __________ |  |
| Meet or communicate at least once yearly with county and multi-municipal planning entities working in and around the watershed Responsible party: ED Results: __________ | Explore with DCNR the options for most efficiently increasing the protected-land buffer around Lackawanna State Park Responsible party: ED and L&WP Committee Chair Results: __________ |  |
| Have a presence at key public meetings relating to land and water conservation in the watershed (ongoing) Responsible party: ED and Executive Committee Results: __________ |
| Meet at least once a year with representatives of each land trust working in and around the watershed (ongoing) Responsible party: ED and Board Results: __________ |